## Sheet1
task_type_or_reject_reason | task_reject_reason | task_last_roadblock | task_type_or_reject_reason | task_type_or_reject_reason
AEP TARS | Unknown | Awaiting Site Visit Completion | AEP TARS | 739
Build Access | CUSTOMER CONDUIT ISSUE | Rejection | Build Access | 41
| Unknown | Awaiting Site Visit Completion | Build Access | 21
|  | Completed Rejection | Build Access | 27
|  | Unknown | Build Access | 228
|  | Waiting Completion of PMG Task | Build Access | 568
|  | Waiting for Build Complete | Build Access | 61
Configuration Templates | Unknown | Unknown | Configuration Templates | 20
Contract Signed | Unknown | Unknown | Contract Signed | 637
Cutover | Unknown | Unknown | Cutover | 23
Design and Build | Unknown | Unknown | Design and Build | 145
IPDP Required | Unknown | Unknown | IPDP Required | 57
|  | Waiting on CSE Response | IPDP Required | 55
|  | Waiting on IPDP/SOW | IPDP Required | 191
|  | Waiting on Sales/PM Response | IPDP Required | 43
Issue Vendor Order BitW | Unknown | Unknown | Issue Vendor Order BitW | 45
PMG | Unknown | Unknown | PMG | 138
|  | Waiting FDWS | PMG | 509
Presales Signed | Unknown | Unknown | Presales Signed | 357
Pricing and Proposal | Unknown | Unknown | Pricing and Proposal | 21
|  | Waiting on IM/IC to set RID | Pricing and Proposal | 43
|  | Waiting on IPDP/SOW | Pricing and Proposal | 26
|  | Waiting on Sales/PM Response | Pricing and Proposal | 60
Rejection due to Pricing and Proposal | SV - CUSTOMER CONDUIT REQUIRED | Waiting on Customer Response | Rejection due to Pricing and Proposal | 58
|  | Waiting on Sales/PM Response | Rejection due to Pricing and Proposal | 46
Rejection due to Validate Customer Account | CUSTOMER CONDUIT ISSUE | Waiting on Customer Response | Rejection due to Validate Customer Account | 24
Revision | FEATURES UPDATED | This Order has Been Revised | Revision | 66
| RID UPDATED | This Order has Been Revised | Revision | 19
Schedule RID | Unknown | Waiting on IM/IC to set RID | Schedule RID | 47
Set NRD | Unknown | Right of Way/Locates | Set NRD | 118
|  | Waiting for Site Visit to Complete | Set NRD | 505
|  | Waiting for other task to be completed | Set NRD | 24
Site Visit Required | SV - CUSTOMER CONDUIT REQUIRED | Rejection | Site Visit Required | 102
| SV - CUSTOMER SUB DUCT ISSUE | Rejection | Site Visit Required | 30
| Unknown | Awaiting Site Visit Completion | Site Visit Required | 105
|  | Completed Rejection | Site Visit Required | 26
|  | Unknown | Site Visit Required | 35
|  | Waiting for Assign Task to Complete | Site Visit Required | 41
Solution Design | Unknown | Unknown | Solution Design | 19
Stage Routers | Unknown | Unknown | Stage Routers | 37
System - 2 Do Not Touch | Unknown | Unknown | System - 2 Do Not Touch | 104
Turn Up Service | Unknown | Unknown | Turn Up Service | 27